## Sheet1
| september | [18 empty] | october | [20 empty] | november | [21 empty] | december
| 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13
Task Name | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T
Preliminary Requirements
Meetings with Customer | bar: F; F; F; F; F; F; F; F; F; F; F
Requirements
Work on Spec | bar: M to F
Submit for Review
Requirements Specification Due | bar: F
Design
Design Work | bar: W to M
Design submit for Review | bar: W
Design Spec Due | bar: Th
Design Presentation | bar: F
Implementation
Team Coding | bar: W to F
Early Prototype Due for Team | bar: M
Code Walkthrough | bar: F
Review Protypes Changes | bar: T to F
Prototype Due | bar: W
Testing
Work on Testing | bar: M to F
User Documentation Due | bar: F
Final System Due
Final Presentation | bar: T
Note on B1: David Hanson: